## 613
Date | 2018-06-13
time in | status | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | csms alerted | Odoo dates changed | initial summary | action items/pending questions
action
2:50 | action | Birkmeyer5306 | dishcraft | curious_salmon43047 | EPS | David | 2018-06-14 | very urgent |  |  |  | these parts were somehow anodized black instead of clear, and one part appears to have a thinner than expected anodize coating. We will discuss the cause/resolution with the MP in the morning on 6/14, but chances are stripping and re-anodizing the parts clear will push out the delivery date. | parts were clear anodized, clear type III just looks black
| action | birkmeyer3940 | dishcraft |  |  | David | [5 empty] | overseas parts sent to local MPs, see what to do with parts
| pending | sanabria7919 | molekule | agreeable_coyote81811 | moddler | David | 2018-06-14 | normal |  |  |  | pickup at moddler delayed till 3 | emil notified
pending responses
| pending | leclerc9755 | apple | extrovert_falcon33804 | goose | David | 2018-06-20 | very urgent | n/a | yes | n/a | 30mm deep holes can only be tapped 24.5mm due to tap depths | pending cusomer OK on design change
| pending | rivetta8409 | Ivo | introvert_cod46533 | Edma tech | David | 2018-06-13 | normal |  | yes | n/a | 18 of 80 parts delivered | find out cause of delay/plan for other parts
10:54 | pending | oshiro1467 | kitty hawk | prickly_kitten73942 | luis fernandez | David | 2018-06-13 | very urgent |  | yes | n/a | thin walls failed during printing | CSMs informed customer, pending customer response
| pending | braman6610 | honeywell | tired_butterfly12930 | productive | David | 2018-06-19 | urgent | n/a | yes |  | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it | pending approval of redacted drawing from customer
| pending | markee1030 | auris | obnoxious_koala71751 | sw | David | 2018-06-14 | urgent | internal | yes | n/a | 2 holes in part, 1 modeled at 2.7mm, other at 2.4mm, both machined to 2.4mm | need to remachine
production resumed
| in production | bangs5143 | lyft | smelly_hare51479 | goose mfg | David | 2018-06-14 | urgent | yes | yes | n/a | part 02-3801268_2018-05-29 has dowel pin installation and anodizing, order of operations was not caught during quoting | part sent from 4D to goose on 6/13, goose to remove pins (if doable), send to duall for quick ano, send back to goose on 6/14 for pin install, then send to customer Parts arrive at goose AM of 6/14, will attempt to remove pins
| in production | dhuldhoya3536 | element sci | soggy_butterfly72014 | norcal mfg | Danielle | 2018-06-14 | normal | yes | yes | yes | delay due to MP missing deep 3D machining feature in part
| in production | zhou3652 | jpl | gentle_salmon81985 | swiss precision | Danielle | 2018-06-15 | normal | no | yes | yes | MP machinist sick. Short staffed.
| in production | birkmeyer3940 | dishcraft | cuddly_canary55370 | swiss precision | Danielle | 2018-06-15 | urgent | no | yes |  | MP machinist sick. Short staffed.
| in production | weiss2021 | instrumental | charming_camel37048 | sw precision | Danielle | 2018-06-18 | normal | no | yes | yes | Fictiv Scheduling issue.
done
12:09 | done | vanderlind8194 | kitty hawk | atomic_butterfly92733 | Sputnik | Danielle | 2018-06-13 | urgent | yes | yes | n/a | had to restart overnight and need more time from pickup | parts had poor surface finish, over/undersized holes. sent to customer
| done | vazquez9943 | zoom systems | obnoxious_kitten44888 | DBK | David | 2018-06-12 | normal | yes | yes | n/a | tapped hole drawings not generated for MP | add improved tap drawing generation to list of product requests parts shipped to customer
| done | marsot7932 | auris | smelly_chicken80598 | swiss precision | David | 2018-06-12 | urgent | yes | n/a | n/a | pickup delayed 2 hours
| done | warner5025 | orca bio | smelly_chicken80598 | swiss precision | David | 2018-06-12 | normal | yes | n/a | n/a | pickup delayed 2 hours
| done | nielsen7358 | sgt inc | rustic_ram47585 | KaD | David | 2018-06-08 | urgent | yes | yes | yes | parts delayed to to lowballing quote | parts shipped
| done | erich8969 | oculus | adorable_hamster16642 | Naslund | David | 2018-06-13 | urgent | yes | yes | yes | scheduling delayed 1 day, delay in answer on if stock thickness could be used | stock thickness approved
| done | pong | auris | rustic_dragonfly68864, clumsy_baboon75519, delerious_goat37080 | Parametric | David | 2018-06-18 | urgent |  |  |  | parts require 316 stainless vs 316L, MP was having initial difficulties sourcing material | pure 316 can't be found, all material is 316/316L dual certified, meaning it is 316 certified. Machining resumed
| done | leclerc3851 | apple | wicked_butterfly93773 | Maxpol | David | 2018-06-19 | very urgent |  |  |  | tolerance can't be promised after head treat | customer accepted inspection only before heat treat
2:37 | done | sanabria7919 |  |  |  | David | [5 empty] | job split across polyjet MPs
| done | wilson4962/wilson8376 | deep space | magical_seahorse25343, Adorable_sheep60551 | duall | David | 2018-06-14 | very urgent |  | AE alerted |  | color of alodine not specified | confirmed alodine should be clear
| done | sathiyaseelan9380 | apple | wild_cod98728 |  | David | 2018-06-14 | very urgent |  |  |  | not scheduled | parts will finish machining on 6/20 in the afternoon at Field Marshall Industries. Andy and Beau will go to inspect the parts, and they they will be direct shipped to Santa Clara Plating for delivery by 6:00pm. finishing should kick off on 6/21, and be expedited for completion by 6/27
|  | marquee1030 | oversized hole
|  | collet1605 | late from DBK
|  | jamespecenka-97372 | tesla | 2018-06-18 | [7 empty] | one day late from M&M. OTIF recorded | Being expidited at Kolsterising, current target is the 18th, SCPL can finish at 3pm on 6/12
|  | burke8199 | cooper perkins | 2018-06-12 |  |  |  |  | picking up today |  |  | reassigned to Edma Tech. Due Tuesday. ST Model done | edma tech both part numbers on wednesday, pending info from CSMs on finishing part early

## 614
Date | 2018-06-14 | [10 empty] | liz@doermarine.com
time in | status | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | csms alerted | Odoo dates changed | initial summary | action items/pending questions
action
| action | collet1605 |  | eager_dragonfly79961 | DBK | David | 2018-06-13 | urgent |  |  |  | late delivery | make sure OTIF and odoo updated
9:26 | action | marsot7932 | auris | agreeable_owl93360 | Swiss Precision | Danielle | 2018-07-14 | urgent | yes | no | n/a | MP running late, pickup at 2pm | record OTIF
|  | gao4363 | ucla | magnificent_cod35587 | Moddler |  | 2018-06-14 | not urgent | yes |  |  | MP mixed up quantities/part | record OTIF, have Moddler print another
pending responses
8:00 | pending | stulc1434 |  | clumsy_piglet11745 | overseas | David | 2018-07-06 |  |  |  |  | MP requests if A3 steel can be used instead of 1018 | alert CSMs
| pending | markee1030 | auris | obnoxious_koala71751 | sw | David | 2018-06-14 | urgent | internal | yes | n/a | 2 holes in part, 1 modeled at 2.7mm, other at 2.4mm, both machined to 2.4mm | no response given, parts were shipped
| pending | leclerc9755 | apple | extrovert_falcon33804 | goose | David | 2018-06-20 | very urgent | n/a | yes | n/a | 30mm deep holes can only be tapped 24.5mm due to tap depths | being canceled, order being replaced
| pending | braman6610 | honeywell | tired_butterfly12930 | productive | David | 2018-06-19 | urgent | n/a | yes |  | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it | pending approval of redacted drawing from customer
production resumed
| action | tarantini8065 | deep space | wandering_penguin91401 | bahre | David | 2018-06-13 | urgent |  | yes | n/a | hole not drilled in part | sent to goose mfg for rework
| action | rivetta8409 | Ivo | introvert_cod46533 | Edma tech | David | 2018-06-13 | normal | on fictiv comms | yes | n/a | 18 of 80 parts delivered | parts will finish monday at noon, due to fictiv ok for partials
| in production | bangs5143 | lyft | smelly_hare51479 | goose mfg | David | 2018-06-14 | urgent | yes | yes | n/a | part 02-3801268_2018-05-29 has dowel pin installation and anodizing, order of operations was not caught during quoting | -pins removed at goose, will send to duall, then back to goose -MAKE DUMMY JOB -tell goose parts will arrive by 4:30pm, or 8:30am -update CSMS
| in production | dhuldhoya3536 | element sci | soggy_butterfly72014 | norcal mfg | Danielle | 2018-06-14 | normal | yes | yes | yes | delay due to MP missing deep 3D machining feature in part | Beau see what info MP would have needed to be able to machine to spec
|  | jamespecenka-97372 | tesla |  |  |  | 2018-06-18 | very urgent | yes | yes |  | parts late due to scheduling delays and machining delays | at kolsterising, attempint to pull in but unsure if doable
done
| closed | lee9264 |  | rad_salmon77712 | madon | David | 2018-06-14 | not urgent |  |  |  | support will be left on part, is uncleanable | support was removed, part is acceptable
10:54 | done | oshiro1467 | kitty hawk | prickly_kitten73942 | luis fernandez | David | 2018-06-13 | very urgent | n/a | yes | n/a | thin walls failed during printing | customer will redesign part, send failed print
2:50 | done | Birkmeyer5306 | dishcraft | curious_salmon43047 | EPS | David | 2018-06-14 | very urgent |  |  |  | these parts were somehow anodized black instead of clear, and one part appears to have a thinner than expected anodize coating. | parts were clear anodized, clear type III ano is just very dark

## 615
Date | 2018-06-15 | [10 empty] | liz@doermarine.com
time in | status | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | csms alerted | Odoo dates changed | initial summary | action items/pending questions
action
pending responses
| pending | braman6610 | honeywell | tired_butterfly12930 | productive | David | 2018-06-19 | urgent | n/a | yes |  | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it | pending ECO from customer, confirmation that part A still on track
| pending | pong3135 | auris | clumsy_baboon75519 | parametric | David | 2018-06-15 | urgent |  | yes | n/a | 11 ready out of 12, 12th done at 3pm | trying to pick up at 8:30am on monday, pending OK from parametric
| pending | markee1030 | auris | obnoxious_koala71751 | sw | David | 2018-06-14 | urgent | internal | yes | n/a | 2 holes in part, 1 modeled at 2.7mm, other at 2.4mm, both machined to 2.4mm | email sent, waiting on lead time
| pending | leclerc9755 | apple | extrovert_falcon33804 | goose | David | 2018-06-20 | very urgent | n/a | yes | n/a | 30mm deep holes can only be tapped 24.5mm due to tap depths | updated files sent to don. Waiting to see cost of ECO, and if customer still wants ECO
8:00 | pending | stulc1434 |  | clumsy_piglet11745 | overseas | David | 2018-07-06 |  |  |  |  | MP requests if A3 steel can be used instead of 1018 | alert CSMs
production resumed
| in production | rivetta8409 | Ivo | introvert_cod46533 | Edma tech | David | 2018-06-13 | normal | on fictiv comms | yes | n/a | 18 of 80 parts delivered | parts will finish monday at noon, due to fictiv ok for partials
| in production | dhuldhoya3536 | element sci | soggy_butterfly72014 | norcal mfg | Danielle | 2018-06-14 | normal | yes | yes | yes | delay due to MP missing deep 3D machining feature in part | Beau see what info MP would have needed to be able to machine to spec
|  | jamespecenka-97372 | tesla |  |  |  | 2018-06-18 | very urgent | yes | yes |  | parts late due to scheduling delays and machining delays | at kolsterising, attempint to pull in but unsure if doable
|  | birkmeyer3940 | dishcraft | cuddly_canary55370 | swiss precision | David | 2018-06-15 | urgent | yes | yes | yes | late at SW | pick up parts on 6/18
|  | zhou3652 | jpl | gentle_salmon81985 | swiss precision | David | 2018-06-15 | normal | yes | yes | yes | late at SW | pick up parts on 6/18
done
9:26 | done | marsot7932 | auris | agreeable_owl93360 | Swiss Precision | Danielle | 2018-07-14 | urgent | yes | no | n/a | MP running late, pickup at 2pm | record OTIF
| done | collet1605 |  | eager_dragonfly79961 | DBK | David | 2018-06-13 | urgent | yes | n/a | n/a | late delivery | make sure OTIF and odoo updated
| done | gao4363 | ucla | magnificent_cod35587 | Moddler | David | 2018-06-14 | not urgent |  |  |  | MP mixed up quantities/part | parts shipped
| done | bangs5143 | lyft | smelly_hare51479 | goose mfg | David | 2018-06-14 | urgent | yes | yes | n/a | part 02-3801268_2018-05-29 has dowel pin installation and anodizing, order of operations was not caught during quoting | -pins removed at goose, will send to duall, then back to goose -MAKE DUMMY JOB -tell goose parts will arrive by 4:30pm, or 8:30am -update CSMS
| done | tarantini8065 | deep space | wandering_penguin91401 | bahre | David | 2018-06-13 | urgent |  | yes | n/a | hole not drilled in part | sent back to customer
| pending | hutchison8711 | verily | sad_duck55689 | goose mfg | David | 2018-06-13 | urgent |  | yes | n/a | customer found two holes unthreaded, no QC was done https://admin.fictiv.com/admin/estimates/0f059a5e-1e79-445f-aa9e-194b38a29abd | goose investigating, no remake needed

## 618
Date | 2018-06-18 | [10 empty] | liz@doermarine.com
time in | status | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | csms alerted | Odoo dates changed | initial summary | action items/pending questions
action
pending responses
| pending | leclerc9755 | apple | extrovert_falcon33804 | goose | David | 2018-06-20 | very urgent | n/a | yes | n/a | 30mm deep holes can only be tapped 24.5mm due to tap depths | updated files sent to don. Waiting to see cost of ECO, and if customer still wants ECO David to sort out internal tracking
production resumed
8:00 | in production | stulc1434 | momentum | clumsy_piglet11745 | overseas | Danielle | 2018-07-06 |  |  | yes |  | 11 | Pending at FeiDi
12:57 | pending | braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | n/a | yes |  | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing sent 6/19 | pending ECO from customer set asana task for partial shipments
12:33 | in production | stinnett5969 | lyft | soggy_marmot49316 | Productive | Danielle | 2018-06-21 | urgent | n/a | yes | n/a | MP requests to add fixturing holes on base of part. Customer said ok.
| in production | pong9984 | auris | delerious_goat37080 | Parametric/DuAll | Danielle |  | urgent | yes | yes | yes | Sent Friday evening to arrive this morning. UPS delay. Will get here Tuesday AM. Supposed to go to DuAll for Media Plasting
| in production | pong3135 | auris | clumsy_baboon75519 | parametric | David | 2018-06-15 | urgent | yes | yes | n/a | 11 ready out of 12, 12th done at 3pm | sent to duall morning 6/18 for same day turn, should be on time to cusotmer
| in production | birkmeyer3940 | dishcraft | cuddly_canary55370 | swiss precision | David | 2018-06-15 | urgent | yes | yes | n/a | late at Swiss | being picked up 6/18, due to other part in order getting anodized, will be on time to customer
| in production | dhuldhoya3536 | element sci | soggy_butterfly72014 | norcal mfg | Danielle | 2018-06-14 | normal | yes | yes | yes | delay due to MP missing deep 3D machining feature in part | Beau see what info MP would have needed to be able to machine to spec
|  | jamespecenka-97372 | tesla |  |  |  | 2018-06-18 | very urgent | yes | yes |  | parts late due to scheduling delays and machining delays | at kolsterising, attempint to pull in but unsure if doable
| in production | vladimirov7314 | ideo | hungry_salmon45416 | fathom | Danielle | 2018-06-19 | normal | yes | yes | yes | parts late due to scheduling delays and print time
done
| in production | zhou3652 | jpl | gentle_salmon81985 | swiss precision | David | 2018-06-15 | normal | yes | yes | yes | late at Swiss | being picked up 6/18, will be one day late, customer notified
| in production | rivetta6267 | Ivo | introvert_cod46533 | Edma tech | David | 2018-06-13 | normal | on fictiv comms | yes | n/a | 18 of 80 parts delivered | parts will finish monday at noon, due to fictiv ok for partials
| in production | markee1030 | auris | obnoxious_koala71751 | sw | David | 2018-06-14 | urgent | internal | yes | n/a | 2 holes in part, 1 modeled at 2.7mm, other at 2.4mm, both machined to 2.4mm | parts remade, set for pickup 6/18

## 619
Date | 2018-06-19 | [10 empty] | liz@doermarine.com
time in | status | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | csms alerted | Odoo dates changed | initial summary | action items/pending questions
action
| action | wilson8376 | deepspace | brave_goat24018 | Sierra Pacific | Danielle | 2018-06-12 | normal | yes | yes | no | parts not tapped, odoo issue | RMA
8:00 | action | stulc1434 | momentum | clumsy_piglet11745 | overseas | Danielle | 2018-07-06 |  |  | yes |  | want 1018 steel | Sync with Cameron on why they are machining from a3
|  | brahic8859 | 219 design | thirsty_alligator |  | Danielle |  |  | yes |  |  |  | follow up v3 to see if on track with 1 day delay
|  |  |  | hollow_camel | [8 empty] | follow up v3 to see if on track for Friday maybe thursday
pending responses
| pending | leclerc9755 | apple | extrovert_falcon33804 | goose | David | 2018-06-20 | very urgent | n/a | yes | n/a | 30mm deep holes can only be tapped 24.5mm due to tap depths | updated files sent to don. Waiting to see cost of ECO, and if customer still wants ECO David to sort out internal tracking
production resumed
| in production | cunningham9437 |  | hollow_camel47259 |  | Danielle | 2018-06-19 | normal | yes | yes | no | Fictiv Scheduling. Expected on Friday. | Check in on V3 6/20 on possibility of Thursday completion
12:33 | in production | stinnett5969 | lyft | soggy_marmot49316 | Productive | Danielle | 2018-06-21 | urgent | n/a | yes | n/a | MP requests to add fixturing holes on base of part. Customer said ok.
12:57 | pending | braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | n/a | yes |  | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19 | Is this a new part? set asana task for partial shipments
3:45 | in production | weiss2021 | dfx machina | charming_camel37048 | SW Precision | Danielle | 2018-06-19 | normal | yes | yes | yes | Material came in late at MP
| in production | pong9984 | auris |  | Parametric/DuAll | Danielle |  | urgent | yes | yes | yes | Sent Friday evening to arrive this morning. UPS delay. Will get here Tuesday AM. Supposed to go to DuAll for Media Plasting
| in production | birkmeyer3940 | dishcraft | cuddly_canary55370 | swiss precision | David | 2018-06-15 | urgent | yes | yes | n/a | late at Swiss | being picked up 6/18, due to other part in order getting anodized, will be on time to customer
| in production | vladimirov7314 | ideo | hungry_salmon45416 | fathom | Danielle | 2018-06-19 | normal | yes | yes | yes | parts late due to scheduling delays and print time
done
|  | jamespecenka-97372 | tesla |  |  |  | 2018-06-18 | very urgent | yes | yes |  | parts late due to scheduling delays and machining delays | at kolsterising, attempint to pull in but unsure if doable
|  | dhuldhoya3536 | element sci | soggy_butterfly72014 | norcal mfg | Danielle | 2018-06-14 | normal | yes | yes | yes | delay due to MP missing deep 3D machining feature in part | Beau see what info MP would have needed to be able to machine to spec
| in production | pong3135 | auris | clumsy_baboon75519 | parametric | David | 2018-06-15 | urgent | yes | yes | n/a | 11 ready out of 12, 12th done at 3pm | sent to duall morning 6/18 for same day turn, should be on time to cusotmer

## 620
Date | 2018-06-20 | [10 empty] | liz@doermarine.com
time in | status | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | csms alerted | Odoo dates changed | initial summary | action items/pending questions
action
8:00 | action | stulc1434 | momentum | clumsy_piglet11745 | overseas | Danielle | 2018-07-06 |  |  | yes |  | want 1018 steel | Sync with Cameron on why they are machining from a3
| action | khau1993 | lyft | clear_butterfly97035 | jarvis | Danielle | 2018-06-22 | urgent | no | no | n/a | need more time. Set pickup to 2pm. | Create internal OTIF
| action | burke2878 | cooper perkins | lyrical_caterpillar59201 | SW | Danielle | 2018-06-19 | very urgent | yes | yes | no | wasn't ready for pickup. Will be ready 6/22 | Call albert at noon to see if compressor ready
| action | warner9659 | orca bio systems | talkative_chicken62217 | LP Manufacturing | Danielle | 2018-06-22 | normal | internal | yes | n/a | untapped holes. | send back to lp, then bring back up for QC. update asana
pending responses
| pending | leclerc9755 | apple | extrovert_falcon33804 | goose | David | 2018-06-20 | very urgent | n/a | yes | n/a | 30mm deep holes can only be tapped 24.5mm due to tap depths | updated files sent to don. Waiting to see cost of ECO, and if customer still wants ECO David to sort out internal tracking
| pending | torrance8441 | auris health | excited_coyote38597 | Sputnik | Danielle | 2018-06-20 | urgent | yes | no | n/a | undersized holes. at sputnik. waiting to see when ready for pickup
| pending | cunningham9437 |  | hollow_camel47259 | V3 | Danielle | 2018-06-19 | normal | yes | yes | no | Fictiv Scheduling. Expected on Friday. | Checking in on V3 6/20 on possibility of Thursday completion
production resumed
| in production | shih1048 | gmail | hidden_giraffe75193 | Casco | Danielle | 2018-06-19 | normal | yes | yes | no | drawing not include in WO bundle. being picked up today
3:45 | in production | weiss2021 | dfx machina | charming_camel37048 | SW Precision | Danielle | 2018-06-19 | normal | yes | yes | yes | Material came in late at MP. Will be ready 6/22
| in production | braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | n/a | yes |  | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19. Parts will be here 6/27
| in production | wilson8376 | deepspace | brave_goat24018 | Sierra Pacific | Danielle | 2018-06-12 | normal | yes | yes | no | parts not tapped, odoo issue. being uber rushed to MP. will be ready friday 11am
| in production | torrance8441 | auris health | cuddly_camel21923 and feral_falcon49493 | Swiss Precision | Danielle | 2018-06-20 | urgent | yes | yes | no | MP short handed. Will be ready 6/21
| in production | brahic8859 | 219 design | thirsty_alligator88506 | V3 | Danielle |  |  | yes | yes | no | all parts kicked up during 3d machine. new due date is 6/25
| in production | birkmeyer3940 | dishcraft | cuddly_canary55370 | swiss precision | David | 2018-06-15 | urgent | yes | yes | n/a | late at Swiss | being picked up 6/18, due to other part in order getting anodized, will be on time to customer
done
|  | pong9984 | auris |  | Parametric/DuAll | Danielle |  | urgent | no | yes | yes | Sent Friday evening to arrive this morning. UPS delay. Will get here Tuesday AM. Supposed to go to DuAll for Media Plasting
|  | dufresne54425 | deep space | benevolent_alligator54425 | CalPol | Danielle | 2018-06-20 | urgent | yes | no | n/a | needs more time.
|  | vladimirov7314 | ideo | hungry_salmon45416 | fathom | Danielle | 2018-06-19 | normal | yes | yes | yes | parts late due to scheduling delays and print time

## 621
Date | 2018-06-21
time in | status | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | csms alerted | Odoo dates changed | initial summary | action items/pending questions
action
8:00 | action | stulc1434 | momentum | clumsy_piglet11745 | overseas | Danielle | 2018-07-06 |  |  | yes |  | want 1018 steel | Sync with Cameron on why they are machining from a3
| action | torrance8441 | auris health | feral_falcon49493 | Swiss Precision | Danielle | 2018-06-20 | urgent | yes | yes | no | MP short handed. Picked up at 1pm on 6/21. Part B out of spec. Being sent back | Send back to Swiss
| action | khau1993 | lyft | clear_butterfly97035 | jarvis | Danielle | 2018-06-22 | urgent | no | yes | n/a | need more time. Set pickup to 2pm. | Create internal OTIF
| action | dufresne3636
pending responses
production resumed
| in production | warner9659 | orca bio systems | talkative_chicken62217 | LP Manufacturing | Danielle | 2018-06-22 | normal | internal | yes | n/a | untapped holes. emailed and called | send back to lp, then bring back up for QC. update asana
| in production | balsamo6860 | momentum | clear_antelope10017 | dbk | Danielle | 2018-06-20 | urgent | yes | yes | no | dbk running late and needs more time to machine
| in production | torrance8441 | auris health | excited_coyote38597 | Sputnik | Danielle | 2018-06-20 | urgent | yes | no | n/a | undersized holes. at sputnik. ready for pickup tomorrow at 11am
| in production | cunningham9437 | hackscience | hollow_camel47259 | V3 | Danielle | 2018-06-19 | normal | yes | yes | no | Fictiv Scheduling. Expected on Friday. | Checking in on V3 6/20 on possibility of Thursday completion
3:45 | in production | weiss2021 | dfx machina | charming_camel37048 | SW Precision | Danielle | 2018-06-19 | normal | yes | yes | yes | Material came in late at MP. Will be ready 6/22
| in production | braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | n/a | yes |  | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19. Parts will be here 6/27
| in production | brahic8859 | 219 design | thirsty_alligator | V3 | Danielle |  |  | yes | yes | no | all parts kicked up during 3d machine. new due date is 6/25
12:33 | in production | stinnett5969 | lyft | soggy_marmot49316 | Productive | Danielle | 2018-06-21 | urgent | n/a | yes | n/a | MP requests to add fixturing holes on base of part. Customer said ok.
| in productio | duckworth8422 | potrero med | extrovert_antelope62661 | SW | Danielle | 2018-06-21 | normal | yes | yes | no | MP machines down till 6/21. Got pushed b/c other very urgent order
| in productio | florimonte1180 | kla-tencor | extrovert_antelope62661 | SW | Danielle | 2018-06-21 | normal | yes | yes | no | MP machines down till 6/21. Got pushed b/c other very urgent order
| in production | kennedy9860 | roastery | charming_falcon39919 | V3 | Danielle | 2018-06-21 | normal | yes | yes | no | got pushed by brahic8859 at v3. will be ready tomorrow
done
| in production | shih1048 | gmail | hidden_giraffe75193 | Casco | Danielle | 2018-06-19 | normal | yes | yes | no | drawing not include in WO bundle. being picked up today
| in production | birkmeyer3940 | dishcraft | cuddly_canary55370 | swiss precision | David | 2018-06-15 | urgent | yes | yes | n/a | being picked up 6/18, due to other part in order getting anodized, will be on time to customer
| in production | wilson8376 | deepspace | brave_goat24018 | Sierra Pacific | Danielle | 2018-06-12 | normal | yes | yes | no | parts not tapped, odoo issue. being uber rushed to MP. will be ready friday 11am
| in production | torrance8441 | auris health | cuddly_camel21923 | Swiss Precision | Danielle | 2018-06-20 | urgent | yes | yes | no | MP short handed. Will be ready 6/21 at 1pm
| in production | burke2878 | cooper perkins | lyrical_caterpillar59201 | SW | Danielle | 2018-06-19 | very urgent | yes | yes | no | wasn't ready for pickup. Will be ready 6/21
|  | leclerc9755 | apple | extrovert_falcon33804 | goose | David | 2018-06-20 | very urgent | n/a | yes | n/a | 30mm deep holes can only be tapped 24.5mm due to tap depths | updated files sent to don. Waiting to see cost of ECO, and if customer still wants ECO David to sort out internal tracking

## 622
Date | 2018-06-22
time in | status | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | csms alerted | Odoo dates changed | initial summary | action items/pending questions
action
| action | stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | [6 empty] | sync up with david | update viking
| action | khau1993 | lyft | clear_butterfly97035 | jarvis | Danielle | 2018-06-22 | urgent | no | yes | n/a | need more time. Set pickup to 2pm. Hold for Monday | Create internal OTIF. Has undersized holes. Send to Jarvis
| action | khau6670 | lyft |  | jarvis | Danielle | 2018-06-27 | urgent | no | yes | n/a | undersized holes. | Create internal OTIF. Has undersized holes. Send to Jarvis uberrush parts to jarvis
| action | torrance8441 | auris health | excited_coyote38597 | Sputnik | Danielle | 2018-06-20 | urgent | yes | no | n/a | undersized holes. at sputnik. 1/4 copies undersized in height. Being remade on 6/25 | Ask Sputnik about eta, set asan tasks
| action | daviswilson | verb surgical | dazzling_goldfish36076 |  | Danielle | 2018-06-26 | very urgent | n/a | yes | n/a | Parts are too small to print. | Should we cancel? How does that work with rest of polyjet prints in the order? Danielle - send to madon
| action | bangs7475 | lyft | enchanting_markhor14416 | Extreme | Danielle | 2018-06-22 | urgent | no | yes | n/a | Missed dowel pin installation on those w/o anodizing. Overnighted on Friday | See when Extreme ready for pickup on Monday to send straight to customer
| action | sherrill8963 |  | 64529 and 34738 | bahre metals | Danielle | 2018-06-22 |  | no | yes | n/a | Bahre sent out parts on time but UPS had delays. Part is a day late so far. | Update csms with tracking numbers add note to odoo
pending responses
production resumed
| in production | dufresne3636 | deep | adorable_nuthatch63904 | Edma Tech | Danielle | 2018-06-20 |  | no | yes | yes | Measurements up by 6%. Emailed to see what happened and get it remachined. | Check file in bundle, find out issue from edma Remachining for Monday
| in production | braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | n/a | yes |  | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19. Parts will be here 6/27 | productive making for 27th
| in production | warner9659 | orca bio systems | talkative_chicken62217 | LP Manufacturing | Danielle | 2018-06-20 | normal | internal. needs external | yes | n/a | untapped holes. emailed and called. At DuAll. Ready today at 1pm. Will be delivered Monday | can be marked done?
| in production | brahic8859 | 219 design | thirsty_alligator | V3 | Danielle |  |  | yes | yes | no | all parts kicked up during 3d machine. new due date is 6/25 | v3 needs more time, Danielle to follow up
12:33 | in production | stinnett5969 | lyft | soggy_marmot49316 | Productive | Danielle | 2018-06-21 | urgent | n/a | yes | n/a | MP requests to add fixturing holes on base of part. Customer said ok. Now at post-processing. Ready 6/25 | customer accepts out of spec parts, follow up productive
| in productio | duckworth8422 | potrero med | extrovert_antelope62661 | SW | Danielle | 2018-06-21 | normal | yes | yes | no | MP machines down till 6/21. Got pushed b/c other very urgent order. Still being worked on. will be ready monday | Call SW to confirm monday
8:00 | in production | stulc1434 | momentum | clumsy_piglet11745 | overseas | Danielle | 2018-07-06 |  |  | yes |  | want 1018 steel | Sync with Cameron on why they are machining from a3
done
| done | balsamo6860 | momentum | clear_antelope10017 | dbk | Danielle | 2018-06-20 | urgent | yes | yes | no | dbk running late and needs more time to machine
| done | torrance8441 | auris health | feral_falcon49493 | Swiss Precision | Danielle | 2018-06-20 | urgent | yes | yes | no | MP short handed. Picked up at 1pm on 6/21. Part B out of spec. Being picked up now
| done | florimonte1180 | kla-tencor | extrovert_antelope62661 | SW | Danielle | 2018-06-21 | normal | yes | yes | no | MP machines down till 6/21. Got pushed b/c other very urgent order. Done
| done | pong4545 | auris | charming_antelope58849-A/ punctual_rabbit52602-A | M&M / DuAll | Danielle | 2018-06-22 | urgent | no | yes | no | set up courier to pick up from customer and then send to DuAll
| done | cunningham9437 | hackscience | hollow_camel47259 | V3 | Danielle | 2018-06-19 | normal | yes | yes | no | Fictiv Scheduling. Expected on Friday. | Checking in on V3 6/20 on possibility of Thursday completion
3:45 | done | weiss2021 | instrumental | charming_camel37048 | SW Precision | Danielle | 2018-06-19 | normal | yes | yes | yes | Material came in late at MP. Will be ready 6/22. Done
| done | kennedy9860 | roastery | charming_falcon39919 | V3 | Danielle | 2018-06-21 | normal | yes | yes | no | got pushed by brahic8859 at v3. will be ready tomorrow
|  |  |  | lyrical_koala68650 | [7 empty] | cancel it!

## 625
Date | 2018-06-25
time in | status | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | csms alerted | Odoo dates changed | initial summary | action items/pending questions
action
| action | khau1993 | lyft | clear_butterfly97035 | jarvis | Danielle | 2018-06-22 | urgent | no | yes | n/a | need more time. Set pickup to 2pm. Hold for Monday | part in spec, send
| action | khau6670 | lyft | irrelevant_worm60752 | jarvis | Danielle | 2018-06-27 | urgent | no | yes | n/a | undersized holes. | part in spec, send
| action | torrance8441 | auris health | excited_coyote38597 | Sputnik | Danielle | 2018-06-20 | urgent | yes | no | n/a | undersized holes. at sputnik. 1/4 copies undersized in height. Being remade on 6/25 | ping jason in odoo
| action | brahic4009 | 219 design | notorious_sheep50231 | HiTech | David | 2018-06-25 | normal | no | yes | n/a | HiTech will be ready for pickup at 3pm. | remake at hi tech or original mp
| action | le2615 | gmail | hilarious_emu83008 | KAD | David | 2018-06-25 | normal | no | yes | no | KAD will be ready by eod instead. | pending pickup time from kad record OTIF
| action | nielsen7358 | sgt inc | rustic_ram47585 | KaD | David | 2018-06-08 | urgent | yes | yes | yes | recieving parts on 6/25 for rework | inform KaD of incoming parts
| action | bangs7475 | lyft | enchanting_markhor14416 | extreme | David | 2018-06-22 | urgent | no | no | no | check that slip fits are made at slip fit | open up holes after ano
|  | heitmann9230 | [9 empty] | order cancelled
|  | cohn4304 | emperical design | agreeable_canary17797 | moddler | David | 2018-06-25 | normal |  | yes | no | late from moddler | record OTIF
| penidng | conroy4755 | aperia tech | clumsy_falcon21417 | russ | David | 2018-06-26 | normal |  | yes | yes | parts delayed a day from MP due to machine failure, can be switched from one day to courier to make it on time to customer | record OTIF
pending responses
| pending | brahic8859 | 219 design | thirsty_alligator88506 | v3 | David | 2018-06-20 | urgent | yes | yes | yes | not ready today | send new CAD, awaiting updated delivery date
| pending | buxton8344 | ximedica | agreeable_ram99741 | B2 | David | 2018-06-26 | urgent |  | yes |  | delayed one day from B2 | pending response from B2 on pulling in pickup time
12:00 | pending | inc5384 |  | Infamous_sheep37382 | moddler | David | 2018-06-25 | normal | n/a | yes | n/a | features below min thickness broke | pending approval from customer to ship
production resumed
| action | stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | David | 2018-06-26 | urgent | no | yes | no | MP questions on model/drawing mismatch | recieved answers to questions
| action | stevenkhau-75853-A-01-A-01-A | lyft | obnoxious_alligator22568 | viking | David | 2018-06-26 | urgent |  | yes |  | material sourcing issues of large parts | pending completion from viking pending response to drawing updates
| in production | dufresne3636 | deep | adorable_nuthatch63904 | Edma Tech | Danielle | 2018-06-20 |  | no | yes | yes | Measurements up by 6%. Emailed to see what happened and get it remachined. | Check file in bundle, find out issue from edma Remachining for Monday
| in production | braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | n/a | yes |  | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19. Parts will be here 6/27 | productive making for 27th
| in production | warner9659 | orca bio systems | talkative_chicken62217 | LP Manufacturing | Danielle | 2018-06-20 | normal | internal. needs external | yes | n/a | untapped holes. emailed and called. At DuAll. Ready today at 1pm. Will be delivered Monday | can be marked done?
| in production | brahic8859 | 219 design | thirsty_alligator | V3 | Danielle |  |  | yes | yes | no | all parts kicked up during 3d machine. new due date is 6/25 | v3 needs more time, Danielle to follow up
12:33 | in production | stinnett5969 | lyft | soggy_marmot49316 | Productive | Danielle | 2018-06-21 | urgent | n/a | yes | n/a | MP requests to add fixturing holes on base of part. Customer said ok. Now at post-processing. Ready 6/25 | customer accepts out of spec parts, follow up productive
| in productio | duckworth8422 | potrero med | extrovert_antelope62661 | SW | Danielle | 2018-06-21 | normal | yes | yes | no | MP machines down till 6/21. Got pushed b/c other very urgent order. Still being worked on. will be ready monday | Call SW to confirm monday
8:00 | in production | stulc1434 | momentum | clumsy_piglet11745 | overseas | Danielle | 2018-07-06 |  |  | yes |  | want 1018 steel | Sync with Cameron on why they are machining from a3
done
| action | daviswilson | verb surgical | dazzling_goldfish36076 |  | Danielle | 2018-06-26 | very urgent | n/a | yes | n/a | Parts are too small to print. | parts printed successfully

## 626
Date | 2018-06-25
time in | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
| brahic4009 | 219 design | notorious_sheep50231 | HiTech | David | 2018-06-25 | normal | no | yes |  | n/a | HiTech will be ready for pickup at 3pm. | remake at hi tech or original mp
added thread
|  |  | notorious_flamingo40954 | calpol | [7 empty] | by the instructions left on top states that I buy 1/16 grounded plate from McMaster. do you want me to not cut down the thickness because the final thickness is .048
| dufrense1818 | [10 empty] | fix tapped holes
| khau1993 | lyft | clear_butterfly97035 | jarvis | Danielle | 2018-06-22 | urgent | no | yes |  | n/a | need more time. Set pickup to 2pm. Hold for Monday | part in spec, send
| khau6670 | lyft | irrelevant_worm60752 | jarvis | Danielle | 2018-06-27 | urgent | no | yes |  | n/a | undersized holes. | part in spec, send
|  |  | infamous_marmot57141 | productive | David |  |  | no | yes | no |  | Wade asked drilled or tapped question in intercom | follow up with wade on communication proceudres
|  |  | suspicous_canary | M&M | David | [6 empty] | model dims don't match drawing dims | have CSMs alert customer
| bangs7475 | lyft | enchanting_markhor14416 | extreme | David | 2018-06-22 | urgent | no | no |  | no | check that slip fits are made at slip fit | create extra payment
| braman6610 | honeywell | tired_butterfly12930 | productive | David |  | urgent |  |  |  |  | lack of tooling caused 1 day delay in part | record OTIF
| dhuldhoya6107 | element sci | weird_hare15997 | Calpol | David | 2018-06-26 | urgent |  | no |  |  | parts A and B have tapered walls that were cut square by accident part C was delayed due to this issue | pick up parts A and B once done, have 2 extra days till order is due record OTIF
| dufresne3636 | deep space | adorable_nuthatch63904 | Edma tech | David | 2018-06-20 |  |  | no | yes | no | remake of part that was scaled down | record OTIF
| balsamo4842 |  | rad_moth57879 | field marshall | David | 2018-06-26 | urgent |  | yes | yes | yes | late 1 day due to issues with very urgent job | record otif
| le2615 | gmail | hilarious_emu83008 | KAD | David | 2018-06-25 | normal | no | yes |  | no | KAD will be ready by eod instead. | parts delivered from Kad at 1pm record OTIF
| cohn4304 | emperical design | agreeable_canary17797 | moddler | David | 2018-06-25 | normal |  | yes |  | no | late from moddler | record OTIF
| conroy4755 | aperia tech | clumsy_falcon21417 | russ | David | 2018-06-26 | normal |  | yes |  | yes | parts delayed a day from MP due to machine failure, can be switched from one day to courier to make it on time to customer | record OTIF
| dufresne3636 | deep | adorable_nuthatch63904 | Edma Tech | Danielle | 2018-06-20 |  | no | yes |  | yes | Measurements up by 6%. Emailed to see what happened and get it remachined. | get response on why part was scaled down
pending responses
| nielsen7358 | sgt inc | rustic_ram47585 | KaD | David | 2018-06-08 | urgent | yes | yes |  | yes | recieving parts on 6/25 for rework | pending estimate of lead time and cost
12:33 | stinnett5969 | lyft | soggy_marmot49316 | Productive | Danielle | 2018-06-21 | urgent | n/a | yes |  | n/a | MP requests to add fixturing holes on base of part. Customer said ok. Now at post-processing. Ready 6/25 | customer accepts out of spec parts, follow up productive
production resumed
| buxton8344 | ximedica | agreeable_ram99741 | B2 | David | 2018-06-26 | urgent |  | yes |  |  | delayed one day from B2 | ready for pickup 6/27
| brahic8859 | 219 design | thirsty_alligator88506 | v3 | David | 2018-06-20 | urgent | yes | yes |  | yes | not ready today | should have 1 set ready by 8am, will provide update then, remaining set later in day. Uber rush drafted to bring straight from v3 to fictiv
| stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | David | 2018-06-26 | urgent | no | yes |  | no | MP questions on model/drawing mismatch | recieved answers to questions
| stevenkhau-75853-A-01-A-01-A | lyft | obnoxious_alligator22568 | viking | David | 2018-06-26 | urgent |  | yes |  |  | material sourcing issues of large parts | pending completion from viking pending response to drawing updates
| braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | no | yes | no | no | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19. Parts will be here 6/28 now. MP ran into issues so is day late. | productive making for 28th
done
8:00 | stulc1434 | momentum | clumsy_piglet11745 | overseas | Danielle | 2018-07-06 |  |  | yes |  |  | want 1018 steel | being machined from 1018 as orderd
| duckworth8422 | potrero med | extrovert_antelope62661 | SW | Danielle | 2018-06-21 | normal | yes | yes |  | no | MP machines down till 6/21. Got pushed b/c other very urgent order. Still being worked on. will be ready monday | done
| warner9659 | orca bio systems | talkative_chicken62217 | LP Manufacturing | Danielle | 2018-06-20 | normal | internal. needs external | yes |  | n/a | untapped holes. emailed and called. At DuAll. Ready today at 1pm. Will be delivered Monday | can be marked done?
| bangs7475 | lyft |  | Extreme | Danielle | 2018-06-22 | urgent | no | yes |  | n/a | Missed dowel pin installation on those w/o anodizing. Overnighted on Friday | parts delivered to customer
| sherrill8963 |  | 64529 and 34738 | bahre metals | Danielle | 2018-06-22 |  | no | yes |  | n/a | Bahre sent out parts on time but UPS had delays. Part is a day late so far. Check tracking numbers listed on DO comment. | arrived
| torrance8441 | auris health | excited_coyote38597 | Sputnik | Danielle | 2018-06-20 | urgent | yes | no |  | n/a | undersized holes. at sputnik. 1/4 copies undersized in height. Being remade on 6/25 | no remake needed
12:00 | inc5384 |  | Infamous_sheep37382 | moddler | David | 2018-06-25 | normal | n/a | yes |  | n/a | features below min thickness broke | customer approved shipping parts
| daviswilson | verb surgical | dazzling_goldfish36076 |  | Danielle | 2018-06-26 | very urgent | n/a | yes |  | n/a | Parts are too small to print. | sent to madon, successfully printed

## 627
Date | 2018-06-25
time in | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
| brahic4009 | 219 design | notorious_sheep50231 | HiTech | David | 2018-06-25 | normal | no | yes |  | n/a | HiTech will be ready for pickup at 3pm. | confirm remake with Beau
| bangs7475 | lyft | enchanting_markhor14416 | extreme | David | 2018-06-22 | urgent | no | no |  | no | check that slip fits are made at slip fit | create extra payment
document
| conroy4755 | aperia tech | clumsy_falcon21417 | russ | David | 2018-06-26 | normal |  | yes | yes | yes | parts delayed a day from MP due to machine failure, can be switched from one day to courier to make it on time to customer | finish recording OTIF
| dufresne3636 | deep | adorable_nuthatch63904 | Edma Tech | Danielle | 2018-06-20 |  | no | yes |  | yes | Measurements up by 6%. Emailed to see what happened and get it remachined. | get response on why part was scaled down record OTIF external
12:33 | stinnett5969 | lyft | soggy_marmot49316 | Productive | Danielle | 2018-06-21 | urgent | yes | yes | yes | n/a | MP requests to add fixturing holes on base of part. Customer said ok. Now at post-processing. Ready 6/25 | customer accepts out of spec parts altert productive to failure
pending responses
| nielsen7358 | sgt inc | rustic_ram47585 | KaD | David | 2018-06-08 | urgent | yes | yes |  | yes | recieving parts on 6/25 for rework | pending estimate of lead time and cost
production resumed
| stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | David | 2018-06-26 | urgent | no | yes |  | no | MP questions on model/drawing mismatch part accidentally gouged
| brahic8859 | 219 design | thirsty_alligator88506 | v3 | David | 2018-06-20 | urgent | yes | yes |  | yes | not ready today | should have 1 set ready by 8am, will provide update then, remaining set later in day. Uber rush drafted to bring straight from v3 to fictiv
| stevenkhau-75853-A-01-A-01-A | lyft | obnoxious_alligator22568 | viking | David | 2018-06-26 | urgent |  | yes |  |  | material sourcing issues of large parts | pending completion from viking pending response to drawing updates
| khau6670 | lyft | irrelevant_worm60752 | jarvis | Danielle | 2018-06-27 | urgent | no | yes |  | n/a | undersized holes. | holes in spec. at ano
done
| buxton8344 | ximedica | agreeable_ram99741 | B2 | David | 2018-06-26 | urgent |  | yes |  |  | delayed one day from B2 | parts picked up 1 day late record OTIF
| cohn4304 | emperical design | agreeable_canary17797 | moddler | David | 2018-06-25 | normal | yes | yes | yes | no | late from moddler | record OTIF
| le2615 | gmail | hilarious_emu83008 | KAD | David | 2018-06-25 | normal | yes | yes |  | no | KAD will be ready by eod instead. | parts delivered from Kad at 1pm record OTIF
| balsamo4842 | momentum | rad_moth57879 | field marshall | David | 2018-06-26 | urgent | yes | yes | yes | yes | late 1 day due to issues with very urgent job | record otif
|  |  | notorious_flamingo40954 | calpol | [7 empty] | by the instructions left on top states that I buy 1/16 grounded plate from McMaster. do you want me to not cut down the thickness because the final thickness is .048 | answered
| tarantini1095 | deep space | [9 empty] | alodine requested after order | asana, odoo delivery order updated
| dhuldhoya6107 | element sci | weird_hare15997 | Calpol | David | 2018-06-26 | urgent | yes | no | yes | yes | parts A and B have tapered walls that were cut square by accident part C was delayed due to this issue | pick up parts A and B once done, have 2 extra days till order is due record OTIF, delayed second time by 20-30 minutes
| parker3211 | kitty hawk | dazzling_narwhal56847 | moddler | David | 2018-06-26 | urgent | yes | no | yes | no | ready at 3pm
| khau1993 | lyft | clear_butterfly97035 | jarvis | Danielle | 2018-06-22 | urgent | no | yes |  | n/a | need more time. Set pickup to 2pm. Hold for Monday | part in spec, send
|  |  | infamous_marmot57141 | productive | David |  |  | no | yes | no | no | Wade asked drilled or tapped question in intercom | holes are thru, not drilled
| marion3945 | JPL | suspicous_canary | M&M | David | 2018-06-28 | urgent | no | yes | no | no | model dims don't match drawing dims | have CSMs alert customer
| marion3945 | JPL | suspicous_canary | M&M | David | 2018-06-28 | urgent | no | yes | no | no | MP had undersized material | customer approved use of alternate material
| braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | yes | yes | no | no | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19. Parts will be here 6/28 now. MP ran into issues so is day late. | productive making for 28th record OTIF

## 628
Date | 2018-06-25
time in | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
| brahic8859 | 219 design | thirsty_alligator88506 | v3 | David | 2018-06-20 | urgent | yes | yes |  | yes | not ready today | get dfm feedback from KAD and V3
| braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | yes | yes | no | no | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19. Parts will be here 6/28 now. MP ran into issues so is day late. | check if came in today
| brahic4009 | 219 design | notorious_sheep50231 | calpol | David | 2018-06-25 | normal | no | yes |  | n/a | calpol also remaking parts, expected ready on 7/2, maybe 6/28 | remake will be ready on 7/3. get the bad part from HiTech to give to customer
| brahic4009 | 219 design | notorious_sheep50231 | HiTech | David | 2018-06-25 | normal | no external | yes |  | n/a | part delayed to 3pm, had a step that was rejected by customer. | remade part still has step on it
| conroy4755 | aperia tech | clumsy_falcon21417 | russ | David | 2018-06-26 | normal |  | yes | yes | yes | parts delayed a day from MP due to machine failure, can be switched from one day to courier to make it on time to customer | finish recording OTIF find backup MP to make parts
| bangs7475 | lyft | enchanting_markhor14416 | extreme | David | 2018-06-22 | urgent | no | no |  | no | check that slip fits are made at slip fit | create extra payment
| daviswilson7420 | verb | sad_hare12682 | fathom | David | 2018-06-28 | urgent |  | yes | yes |  | part A (20180622_wiring_prt008998) not ready till 629 | inform
| daviswilson7420 | verb | hunting_camel18790 | fathom | David | 2018-06-28 | urgent |  | yes | yes |  | part C (2018-06-11_wiring_prt007208005884005436) and D (20180622_wiring_prt006987) not ready till 6/29 | inform
document
| tighe8128 | JPL | dazzling_emu52660 | edma | David | 2018-06-28 | urgent |  | yes |  |  | not picked up due to 3D machined area not passing surface finish | being reworked for pickup at 3 record OTIF
| dufresne1818 | deep space | adorable_nuthatch63904 | Edma tech | David | 2018-06-20 | urgent | no | yes | no | no | fix tapped holes | record OTIF on fictiv
| dufresne3636 | deep | adorable_nuthatch63904 | Edma Tech | Danielle | 2018-06-20 |  | no | yes |  | yes | Measurements up by 6%. Emailed to see what happened and get it remachined. | get response on why part was scaled down check our files record OTIF external
12:33 | stinnett5969 | lyft | soggy_marmot49316 | Productive | Danielle | 2018-06-21 | urgent | yes | yes | yes | n/a | MP requests to add fixturing holes on base of part. Customer said ok. Now at post-processing. Ready 6/25 | customer accepts out of spec parts altert productive to failure
| stevenkhau-75853-A-01-A-01-A | lyft | obnoxious_alligator22568 | viking | David | 2018-06-26 | urgent |  | yes |  |  | material sourcing issues of large parts | pending completion from viking pending response to drawing updates
pending responses
| karafillis7662 | jpl | gentle_koala54858 | rapid turn | David | 2018-06-27 | urgent | yes | yes | yes | yes | delayed one day | pending response on pickup
| maniktala2941 |  | groovy_nuthatch65485 | max dirat | David | 2018-06-28 | normal |  |  |  |  | 3D file issue | pending response from CSMs
| khau9994 | lyft | smelly_butterfly35083 |  | David |  | urgent |  |  | yes |  | pins inserted in part needing ano | yorke can pull and install pins in both parts pending response from CSM
| nielsen7358 | sgt inc | rustic_ram47585 | KaD | David | 2018-06-08 | urgent | yes | yes |  | yes | recieving parts on 6/25 for rework | pending estimate of lead time and cost
production resumed
| murphy3939 |  | notorious_flamingo40954 | calpol | David | 2018-06-28 | urgent |  | yes | yes |  | parts not ready for pickup at 11am | pickup today from calpol record OTIF
| stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | David | 2018-06-26 | urgent | no | yes |  | no | MP questions on model/drawing mismatch part accidentally gouged
| khau6670 | lyft | irrelevant_worm60752 | jarvis | Danielle | 2018-06-27 | urgent | no | yes |  | n/a | undersized holes. | holes in spec. at ano
| delacruz6543 | fictiv | weird_piglet10568 | madon | David | 2018-06-28 | not urgent | no | yes | yes | yes | too long to print and dry in 1 day, will be picked up a day late | "is done printing and in the bath. After speaking to Danielle the job will be ready for pickup Friday June 29 2018 "
done
|  |  | atomic_canary29249_feidi | feidi | David | [6 empty] | feidi planning to switch from CNC to sheet metal | told feidi to make to stock thickness but machine edges

## 629
Date | 2018-06-25
time in | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
| cardinal2140 | [10 empty] | opk_ring_s11_5_r1.step and opk_ring_s9_5_r1.step sent to wrong address, need to remake | schedule remake
| malanowski1523 | [10 empty] | 110-002974_rev02_protective_cone.step part halves fused togeather, resend to moddler, reference part 100-001331 for previous prints | schedule remake to moddler
| murphy3939 |  | notorious_flamingo40954 | calpol | David | 2018-06-28 | urgent |  | yes | yes |  | parts not ready for pickup at 11am | record OTIF further delay, notify CSMs
|  |  | sad_alligator18595 | calpol | [7 empty] | late pickup | CSMs notified, document and follow up on what is complete for today
|  |  | sad_marmot83349 | calpol | [7 empty] | late pickup | CSMs notified, document and follow up
| sloth | verb | [9 empty] | pending approval on change | talk with franklin
| braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | yes | yes | no | no | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19. Parts will be here 6/28 now. MP ran into issues so is day late. | check if came in today
| brahic4009 | 219 design | notorious_sheep50231 | calpol | David | 2018-06-25 | normal | no | yes |  | n/a | calpol also remaking parts, expected ready on 7/2, maybe 6/28 | remake will be ready on 7/3. get the bad part from HiTech to give to customer
| brahic4009 | 219 design | notorious_sheep50231 | HiTech | David | 2018-06-25 | normal | no external | yes |  | n/a | part delayed to 3pm, had a step that was rejected by customer. | remade part still has step on it
| conroy4755 | aperia tech | clumsy_falcon21417 | russ | David | 2018-06-26 | normal |  | yes | yes | yes | parts delayed a day from MP due to machine failure, can be switched from one day to courier to make it on time to customer | finish recording OTIF find backup MP to make parts
| bangs7475 | lyft | enchanting_markhor14416 | extreme | David | 2018-06-22 | urgent | no | no |  | no | check that slip fits are made at slip fit | create extra payment
document
| tighe8128 | JPL | dazzling_emu52660 | edma | David | 2018-06-28 | urgent |  | yes |  |  | not picked up due to 3D machined area not passing surface finish | part A picked up on 6/29 record OTIF
| dufresne1818 | deep space | adorable_nuthatch63904 | Edma tech | David | 2018-06-20 | urgent | no | yes | no | no | fix tapped holes | record OTIF on fictiv
| stevenkhau-75853-A-01-A-01-A | lyft | obnoxious_alligator22568 | viking | David | 2018-06-26 | urgent |  | yes |  |  | material sourcing issues of large parts | pending completion from viking pending response to drawing updates
| daviswilson7420 | verb | sad_hare12682 | fathom | David | 2018-06-28 | urgent |  | yes | yes |  | part A (20180622_wiring_prt008998) not ready till 629 | confirm if parts were picked up and sent
| daviswilson7420 | verb | hunting_camel18790 | fathom | David | 2018-06-28 | urgent |  | yes | yes |  | part C (2018-06-11_wiring_prt007208005884005436) and D (20180622_wiring_prt006987) not ready till 6/29 | inform
| nielsen7358 | sgt inc | rustic_ram47585 | KaD | David | 2018-06-08 | urgent | yes | yes |  | yes | recieving parts on 6/25 for rework | parts sent back to customer, make dummy job to pay KaD
pending responses
production resumed
| stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | David | 2018-06-26 | urgent | no | yes |  | no | MP questions on model/drawing mismatch part accidentally gouged
| delacruz6543 | fictiv | weird_piglet10568 | madon | David | 2018-06-28 | not urgent | no | yes | yes | yes | too long to print and dry in 1 day, will be picked up a day late | "is done printing and in the bath. After speaking to Danielle the job will be ready for pickup Friday June 29 2018 "
done
| khau9994 | lyft | smelly_butterfly35083 |  | David |  | urgent |  |  | yes |  | pins inserted in part needing ano | yorke can pull and install pins in both parts pending response from CSM
| khau6670 | lyft | irrelevant_worm60752 | jarvis | Danielle | 2018-06-27 | urgent | no | yes |  | n/a | undersized holes. | holes in spec. at ano
| maniktala2941 |  | groovy_nuthatch65485 | max dirat | David | 2018-06-28 | normal |  |  |  |  | 3D file issue | pending response from CSMs
| karafillis7662 | jpl | gentle_koala54858 | rapid turn | David | 2018-06-27 | urgent | yes | yes | yes | yes | delayed one day | pending response on pickup
| dufresne3636 | deep | adorable_nuthatch63904 | Edma Tech | Danielle | 2018-06-20 |  | no | yes |  | yes | Measurements up by 6%. Emailed to see what happened and get it remachined. | get response on why part was scaled down check our files record OTIF external
12:33 | stinnett5969 | lyft | soggy_marmot49316 | Productive | Danielle | 2018-06-21 | urgent | yes | yes | yes | n/a | MP requests to add fixturing holes on base of part. Customer said ok. Now at post-processing. Ready 6/25 | customer accepts out of spec parts altert productive to failure
| brahic8859 | 219 design | thirsty_alligator88506 | v3 | David | 2018-06-20 | urgent | yes | yes |  | yes | not ready today | get dfm feedback from KAD and V3
|  |  | atomic_canary29249_feidi | feidi | David | [6 empty] | feidi planning to switch from CNC to sheet metal | told feidi to make to stock thickness but machine edges
|  |  | wicked_coyote78983 | sputnik | David | 2018-07-02 | urgent | no | no | no | no | "I noticed that there are a few holes for a tap M4 helicoil inserts needed. I assume you ll be doing this in -house. We will tap all M4 holes noted." | confirmed that parts should be tapped for helicoils, but no installation
| smith3053 | auris | delerious_cow10079 | feidi | David | 2018-07-11 | urgent | no |  | no | no | parts not media blasted in feidi (as they shouldn't be) and extra parts sent
| warner7643 |  | punctual_caterpillar33568 | casco | david | 2018-07-03 | normal | no | no | no | no | "Do you know if there is any flatness requirement on this plate?" | confimed no flatness requirements
| parkes4398 | bellwether | clear_duck44947 | deep | David | 2018-07-03 | urgent | no | no | no | no | "Can you please clarify on part B the call out for the crosshole" | confirmed no callout required for cross hole

## 72
Date | 2018-06-25
time in | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
| brahic4009 | 219 design | notorious_sheep50231 | calpol | Danielle | 2018-06-25 | normal | no | yes |  | n/a | calpol also remaking parts, expected ready on 7/2, maybe 6/28 | remake will be ready on 7/3. get the bad part from HiTech to give to customer. Move calpol pickup to late for this. David to follow up with CalPol
| brahic4009 | 219 design | notorious_sheep50231 | HiTech | David | 2018-06-25 | normal | no external | yes |  | n/a | part delayed to 3pm, had a step that was rejected by customer. | remade part still has step on it
| conroy4755 | aperia tech | clumsy_falcon21417 | russ | Danielle | 2018-06-26 | normal |  | yes | yes | yes | parts delayed a day from MP due to machine failure, can be switched from one day to courier to make it on time to customer | finish recording OTIF on russ and fictiv for communications document double jobs for one order.
| meissner7109 |  | suspicious_ram66121 | RYT | Danielle
| nielsen7358 | sgt inc | rustic_ram47585 | KaD | David | 2018-06-08 | urgent | yes | yes |  | yes | recieving parts on 6/25 for rework | parts sent back to customer, make dummy job to pay KaD $205 (confirm price with Brian)
document
| murphy3939 |  | notorious_flamingo40954 | calpol | Danielle | 2018-06-28 | urgent |  | yes | yes |  | parts not ready for pickup at 11am | record OTIF further delay, notify CSMs
| daviswilson7420 | verb | hunting_camel18790 | fathom | David | 2018-06-28 | urgent |  | yes | yes |  | part C (2018-06-11_wiring_prt007208005884005436) and D (20180622_wiring_prt006987) not ready till 6/29. marked as done | confirm if parts were picked up and sent
| daviswilson7420 | verb | sad_hare12682 | fathom | David | 2018-06-28 | urgent |  | yes | yes |  | part A (20180622_wiring_prt008998) not ready till 629. marked as done
| dhuldhoya3372 |  | sad_alligator18595 | calpol | Danielle | [6 empty] | late pickup | CSMs notified, document and follow up on what is complete for today
| mcintyre5905 |  | sad_marmot83349 | calpol | Danielle | [6 empty] | late pickup | CSMs notified, document and follow up
| tighe8128 | JPL | dazzling_emu52660 | edma | David | 2018-06-28 | urgent |  | yes |  |  | not picked up due to 3D machined area not passing surface finish | part A picked up on 6/29 record OTIF
| dufresne1818 | deep space | adorable_nuthatch63904 | Edma tech | David | 2018-06-20 | urgent | no | yes | no | no | fix tapped holes | record OTIF on fictiv
| stevenkhau-75853-A-01-A-01-A | lyft | obnoxious_alligator22568 | viking | David | 2018-06-26 | urgent |  | yes |  |  | material sourcing issues of large parts | pending completion from viking pending response to drawing updates
pending responses
production resumed
| cannistraro4221 | miroculus | introvert_cow25995 | swiss | Danielle | [6 empty] | part out of spec with oversized fillets, sent back to swiss for fix. ready for pickup | inform swiss of what needs to be fixed. Workspace
| stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | David | 2018-06-26 | urgent | no | yes |  | no | MP questions on model/drawing mismatch part accidentally gouged
| cardinal2140 |  |  |  | Danielle | [6 empty] | opk_ring_s11_5_r1.step and opk_ring_s9_5_r1.step sent to wrong address, need to remake, see asana task. rework4037
| braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | yes | yes | no | no | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19. Parts will be here 6/28 now. MP ran into issues so is day late. | check if came in today
| malanowski1523 |  |  |  | Danielle | [6 empty] | 110-002974_rev02_protective_cone.step part halves fused togeather, resend to moddler, reference part 100-001331 for previous prints, see asana task | schedule remake to moddler
| delacruz6543 | fictiv | weird_piglet10568 | madon | David | 2018-06-28 | not urgent | no | yes | yes | yes | too long to print and dry in 1 day, will be picked up a day late | "is done printing and in the bath. After speaking to Danielle the job will be ready for pickup Friday June 29 2018 "
done

## 75
Date | 2018-06-25
time in | order | customer | job | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
action | malanowski1523 |  |  |  | Danielle | [6 empty] | 110-002974_rev02_protective_cone.step part halves fused togeather, resend to moddler, reference part 100-001331 for previous prints, see asana task | schedule 11 more to moddler
action | nielsen7358 | sgt inc | rustic_ram47585 | KaD | David | 2018-06-08 | urgent | yes | yes |  | yes | recieving parts on 6/25 for rework | parts sent back to customer, make dummy job to pay KaD $205 (confirm price with Brian)
document
| murphy3939 |  | notorious_flamingo40954 | calpol | Danielle | 2018-06-28 | urgent |  | yes | yes |  | parts not ready for pickup at 11am | record OTIF further delay, notify CSMs
| daviswilson7420 | verb | hunting_camel18790 | fathom | David | 2018-06-28 | urgent |  | yes | yes |  | part C (2018-06-11_wiring_prt007208005884005436) and D (20180622_wiring_prt006987) not ready till 6/29. marked as done | confirm if parts were picked up and sent
| daviswilson7420 | verb | sad_hare12682 | fathom | David | 2018-06-28 | urgent |  | yes | yes |  | part A (20180622_wiring_prt008998) not ready till 629. marked as done
| dhuldhoya3372 |  | sad_alligator18595 | calpol | Danielle | [6 empty] | late pickup | CSMs notified, document and follow up on what is complete for today
| mcintyre5905 |  | sad_marmot83349 | calpol | Danielle | [6 empty] | late pickup | CSMs notified, document and follow up
| tighe8128 | JPL | dazzling_emu52660 | edma | David | 2018-06-28 | urgent |  | yes |  |  | not picked up due to 3D machined area not passing surface finish | part A picked up on 6/29 record OTIF
| dufresne1818 | deep space | adorable_nuthatch63904 | Edma tech | David | 2018-06-20 | urgent | no | yes | no | no | fix tapped holes | record OTIF on fictiv
| stevenkhau-75853-A-01-A-01-A | lyft | obnoxious_alligator22568 | viking | David | 2018-06-26 | urgent |  | yes |  |  | material sourcing issues of large parts | pending completion from viking pending response to drawing updates
| delacruz6543 | fictiv | weird_piglet10568 | madon | David | 2018-06-28 | not urgent | no | yes | yes | yes | too long to print and dry in 1 day, will be picked up a day late | "is done printing and in the bath. After speaking to Danielle the job will be ready for pickup Friday June 29 2018 "
pending responses
pending | olsen2185 | black more inc | useless_sheep15498 | NorCal | Danielle | 2018-07-03 | normal | internal so far |  |  |  | Godspeed got confused picking up the parts from the MP. Had delayed pickup. Parts are out of spec with oversized holes
pending | conroy2967 | aperia tech | brave_antelope94345 | Jarvis | Danielle | 2018-07-05 | urgent | internal so far |  |  |  | One copy of a part had a slanted feature. Waiting on CSM to confirm with customer so we can ship out
production resumed
| stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | David | 2018-06-26 | urgent | no | yes |  | no | MP questions on model/drawing mismatch part accidentally gouged
in production | birkmeyer6589 | dishcraft | clever_salmon59697 | Circuit Case | Danielle | 2018-07-05 | urgent | yes | yes |  |  | Both A and B were out of spec. A had untapped holes and B hand undersized holes
in production | cannistraro4221 | miroculus | introvert_cow25995 | Swiss | Danielle | 2018-07-03 | normal | yes |  |  |  | Fillets in one of the parts were too big and needed to be reworked
in production | parkes4398 | bellwether | smelly_penguin41632 | Swiss | Danielle | 2018-07-06 | urgent |  | yes | yes |  | Special tools didn't come in on time and needs more time to machine
in production | whiting1875 | intuitive | curious_dragonfly74290 | LP | Danielle | 2018-07-05 | urgent |  |  |  |  | at risk b/c DuAll closed. Sent to 4D
in production | risk1374 | ibm | prickly_nuthatch63091 | Casco | Danielle | 2018-07-03 | urgent |  |  |  |  | late pickup from MP. In FedEx limbo b/c DuAll closed. Couldn't reroute
done
done | brahic4009/rework6964 | 219 design | agreeable_emu69912 | CalPol | Danielle | 2018-06-25 | normal | yes | yes | yes | yes | Calpol had done this before. expected 7/2. Received 6/5
done | brahic4009 | 219 design | notorious_sheep50231 | HiTech | David | 2018-06-25 | normal | yes | yes | yes | yes | Part Delayed and had a step in the part that isn't in the design nor is it acceptable to the customer. They remade and it still came out the same. | Beau - follow up after they're back in office
done | conroy4755 | aperia tech | clumsy_falcon21417 | Russ Precision | Danielle | 2018-06-15 | normal | yes | yes |  |  | Machine failure at MP.
done | stephens9823 | intuitive | wicked_coyote78983 | Sputnik | Danielle | 2018-07-02 | urgent | yes |  |  |  | Out of spec with undersized holes
done | lee7908 | intuitive | wicked_coyote78983 | Sputnik | Danielle | 2018-07-02 | urgent | yes |  |  |  | Out of spec with oversized taps. Had them put helicoils
done | markus2351 | tesla | punctual_moth86706 | MLS | Danielle | 2018-07-03 | very urgent | yes |  |  |  | MP messed up in final operation. Needed one more day.
done | boergens3659 | paradromics | talkative_rabbit69098 | Parametric | Danielle | 2018-07-03 | very urgent | yes |  |  |  | Got pushed to 7/5 b/c of scheduling. MP needs late pickup
done | tarantini8686 | deep space | gullible_ostrich91717 | CalPol | Danielle | 2018-07-02 | urgent | yes |  |  |  | Delayed due to overloading
done | hill1209 | intuitive | benevolent_sheep75401 | CalPol | Danielle | 2018-07-02 | urgent | yes |  |  |  | Delayed due to overloading
done | cardinal2140 |  |  |  | Danielle | [6 empty] | opk_ring_s11_5_r1.step and opk_ring_s9_5_r1.step sent to wrong address, need to remake, see asana task. rework4037
done | braman6610 | honeywell | tired_butterfly12930 | productive | Danielle | 2018-06-19 | urgent | yes | yes | no | no | no drawing for part B was uploaded by CSMs, drawing given by customer is for a different part with extensive redlines on it. Drawing and part file sent 6/19. Parts will be here 6/28 now. MP ran into issues so is day late. | check if came in today

## 76
time in | sales order | account | work order | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
document
| stevenkhau-75853-A-01-A-01-A | lyft | obnoxious_alligator22568 | viking | David | 2018-06-26 | urgent |  | yes |  |  | material sourcing issues of large parts | pending completion from viking pending response to drawing updates
pending responses
pending | olsen2185 | black more inc | useless_sheep15498 | NorCal | Danielle | 2018-07-03 | normal | internal so far |  |  |  | Godspeed got confused picking up the parts from the MP. Had delayed pickup. Parts are out of spec with oversized holes
pending | bangs3264 | lyft | drunk_marmot92489 | Maxpol | Danielle |  |  | n/a | yes | n/a | n/a | Needs laser etching for part number and revision, but has anodizing after that may make it difficult to see. MP is wondering if he can just engrave
production resumed
| stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | David | 2018-06-26 | urgent | no | yes |  | no | MP questions on model/drawing mismatch part accidentally gouged
in production | copeland1115 | tesla | rad_puppy38039 | M&M | Danielle | 2018-07-06 | very urgent | internal |  |  |  | UPS delayed. Will courier on Monday
in production | birkmeyer6589 | dishcraft | clever_salmon59697 | Circuit Case | Danielle | 2018-07-05 | urgent | yes | yes |  |  | Both A and B were out of spec. A had untapped holes and B hand undersized holes
in production | parkes4398 | bellwether | smelly_penguin41632 | Swiss | Danielle | 2018-07-06 | urgent | internal | yes | yes |  | Special tools didn't come in on time and needs more time to machine
in production | risk1374 | ibm | prickly_nuthatch63091 | Casco | Danielle | 2018-07-03 | urgent | internal |  |  |  | late pickup from MP. In FedEx limbo b/c DuAll closed. Couldn't reroute
in production | anselmmak-72505 | tesla | extrovert_sheep67275 | Deep Machine | Mo | 2018-07-05 | normal | ? | ? | ? | ? | water jet part. various qc issues. large CB that made hole oversized
| mauriello6987 |  | punctual_caterpillar91611 | Justin Barcelos | Danielle | 2018-07-06 | not urgent | n/a | no |  |  | Vendor due date didn't update when sales order dates were changed. Picking up part on 7/6. May have burn marks. New one in the works
in production | malanowski1523 |  |  |  | Danielle |  |  | n/a |  |  |  | 110-002974_rev02_protective_cone.step part halves fused together, resend to moddler, reference part 100-001331 for previous prints, see asana task | schedule 11 more to moddler
done
done | nielsen7358 | sgt inc | rustic_ram47585 | KaD | David | 2018-06-08 | urgent | yes | yes |  | yes | recieving parts on 6/25 for rework, Made payment to KAD
done | cannistraro4221 | miroculus | introvert_cow25995 | Swiss | Danielle | 2018-07-03 | normal | yes |  |  |  | Fillets in one of the parts were too big and needed to be reworked
done | ang2550 | auris | clumsy_ostrich17574 | Moddler | Danielle | 2018-07-05 | urgent |  |  |  |  | Part B with long print and dry time. has later pickup
done | conroy2967 | aperia tech | brave_antelope94345 | Jarvis | Danielle | 2018-07-05 | urgent | internal so far |  |  |  | One copy of a part had a slanted feature. Custome is ok with it
done | whiting1875 | intuitive | curious_dragonfly74290 | LP | Danielle | 2018-07-05 | urgent | external |  |  |  | at risk b/c DuAll closed. Sent to 4D
| daviswilson7420 | verb | hunting_camel18790 | fathom | David | 2018-06-28 | urgent | int/ext | yes | yes |  | part C (2018-06-11_wiring_prt007208005884005436) and D (20180622_wiring_prt006987) not ready till 6/29. marked as done | confirm if parts were picked up and sent
| daviswilson7420 | verb | sad_hare12682 | fathom | David | 2018-06-28 | urgent | int/ext | yes | yes |  | part A (20180622_wiring_prt008998) not ready till 629. marked as done
| murphy3939 |  | notorious_flamingo40954 | calpol | Danielle | 2018-06-28 | urgent | yes | yes | yes |  | parts not ready for pickup at 11am | record OTIF further delay, notify CSMs
| tighe8128 | JPL | dazzling_emu52660 | edma | David | 2018-06-28 | urgent | yes | yes |  |  | not picked up due to 3D machined area not passing surface finish | part A picked up on 6/29 record OTIF
| dhuldhoya3372 |  | sad_alligator18595 | calpol | Danielle |  |  | yes |  |  |  | late pickup | CSMs notified, document and follow up on what is complete for today
| mcintyre5905 |  | sad_marmot83349 | calpol | Danielle |  |  | yes |  |  |  | late pickup | CSMs notified, document and follow up
| delacruz6543 | fictiv | weird_piglet10568 | madon | David | 2018-06-28 | not urgent | yes | yes | yes | yes | too long to print and dry in 1 day, will be picked up a day late | "is done printing and in the bath. After speaking to Danielle the job will be ready for pickup Friday June 29 2018 "
| dufresne1818 | deep space | adorable_nuthatch63904 | Edma tech | David | 2018-06-20 | urgent | yes | yes | no | no | fix tapped holes | record OTIF on fictiv

## 79
time in | sales order | account | work order | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
pending responses
pending | olsen2185 | black more inc | useless_sheep15498 | NorCal | Danielle | 2018-07-03 | normal | internal so far |  |  |  | Godspeed got confused picking up the parts from the MP. Had delayed pickup. Parts are out of spec with oversized holes
pending | anselmmak-72505 | tesla | extrovert_sheep67275 | Deep Machine | Mo | 2018-07-05 | normal | ? | ? | ? | ? | water jet part. various qc issues. large CB that made hole oversized
production resumed
| stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | David | 2018-06-26 | urgent | no | yes |  | no | MP questions on model/drawing mismatch part accidentally gouged
in production | bangs3264 | lyft | drunk_marmot92489 | Maxpol | Danielle |  |  | n/a | yes | n/a | n/a | Needs laser etching for part number and revision, but has anodizing after that may make it difficult to see. MP is engraving part number
in production | lang6581 | propelland | wicked_chicken72262 | Radius | Danielle | 2018-07-10 | normal | no | yes | no | no | MP had blackout over weekend. Large prints will be done Wednesday
in production | copeland1115 | tesla | rad_puppy38039 | M&M | Danielle | 2018-07-06 | very urgent | internal |  |  |  | UPS delayed. Will courier on Monday | root cause dings on parts
in production | parkes4398 | bellwether | smelly_penguin41632 | Swiss | Danielle | 2018-07-06 | urgent | int/ext | yes | yes |  | Special tools didn't come in on time and needs more time to machine.
in production | risk1374 | ibm | prickly_nuthatch63091 | Casco | Danielle | 2018-07-03 | urgent | internal |  |  |  | late pickup from MP. In FedEx limbo b/c DuAll closed. Couldn't reroute
in production | malanowski1523/rework6886 |  |  |  | Danielle |  |  | n/a |  |  |  | 110-002974_rev02_protective_cone.step part halves fused together, resend to moddler, reference part 100-001331 for previous prints, see asana task
document
| stevenkhau-75853-A-01-A-01-A | lyft | obnoxious_alligator22568 | viking | David | 2018-06-26 | urgent |  | yes |  |  | material sourcing issues of large parts | pending completion from viking pending response to drawing updates
| maclaren2401 | hobbit view | wandering_robin31571 | Madon | Danielle | 2018-07-09 | normal |  | n/a | yes | n/a |  | log internal OTIF.
done
done | birkmeyer6589 | dishcraft | clever_salmon59697 | Circuit Case | Danielle | 2018-07-05 | urgent | yes | yes |  |  | Both A and B were out of spec. A had untapped holes and B hand undersized holes
done | mauriello6987 |  | punctual_caterpillar91611 | Justin Barcelos | Danielle | 2018-07-06 | not urgent | n/a | no |  |  | Vendor due date didn't update when sales order dates were changed. Picking up part on 7/6. May have burn marks. New one in the works
| mcleod2001 | bossa nova | rad_penguin75416 | Max Dirat | Danielle | 2018-07-09 | normal | yes | yes | no | n/a | Tabs on part A keep breaking off during print. MP will give us what he has. Asking customer to see if printing in parts is ok

## 710 and 711
time in | sales order | account | work order | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
| mcdaid5992 | kitty hawk | rad_orca84521_feidi | bole | Danielle | 2018-07-19 | urgent | no | no | n/a | no | Rona said this would be late | ask rona why there is a delay already
| gagne2485 | aeva | obnoxious_bear87015_feidi | shouzheng | Danielle | 2018-07-18 | very urgent | n/a | no | n/a | n/a | Check asana. | thread checkers to feidi
| sweet1206 | apple | enchanting_ram65551 | mach 1 | David | 2018-07-11 | very urgent |  | yes | n/a | no | 3mm posts are undersized, measuring 2.85mm | customer accepted parts record OTIF noted by david
pending responses
| anselmmak-72505 | tesla | extrovert_sheep67275 | Deep Machine | Mo | 2018-07-05 | normal | ? | ? | ? | ? | water jet part. various qc issues. large CB that made hole oversized | pending customer response
production resumed
| stulc8482 | momentum | suspicious_seahorse30661 |  | Danielle | 2018-07-16 | very urgent | n/a | yes | n/a | n/a | Drawing calls out 2x of grooves, but there's only one in the model. Let customer know of type and MP proceeded with production
| bangs3264 | lyft | drunk_marmot92489 | Maxpol | Danielle | 2018-07-17 | urgent | n/a | yes | n/a | n/a | Needs laser etching for part number and revision, but has anodizing after that may make it difficult to see. MP is engraving part number
| goodwin4678 | vector-launch | tender_penguin49682 | Sierra Pacific | Danielle | 2018-07-13 | normal | n/a | yes | n/a | n/a | MP wondering if threads go on one surfae or two on a shaft. There's a break where there's a thinner diameter. Threads go on both surfaces
| goodwin4638 | vector-launch | clumsy_coyote34223 | Mach 1 | Danielle | 2018-07-13 | very urgent | n/a | yes | n/a | n/a | MP wondering if they can increase internal radii from 0.1" to 0.125". Customer said ok.
document
| maclaren2401 | hobbit view | wandering_robin31571 | Madon | Danielle | 2018-07-09 | normal |  | n/a | yes | n/a | Support left on the part so it needed to go back in the bath. MP needed later pickup | log internal OTIF.
| agozzino6930 | lumasense inc | gullible_nuthatch48170 | fathom | Danielle | 2018-07-10 | normal | int | yes | yes | n/a
| agozzino3617 | lumasense inc | adorable_coyote44528 | fathom | Danielle | 2018-07-10 | normal | int | yes | yes | n/a
| lang6581 | propelland | wicked_chicken72262 | Radius | Danielle | 2018-07-10 | normal | no | yes | no | no | MP had blackout over weekend. Large print will be done Wednesday. Ficitv validated DO prematurely. Pickup wasn't set for Wednesday. | log internal and external OTIF on Radius and Fictiv
| mcleod2001 | bossa nova | rad_penguin75416 | Max Dirat | Danielle | 2018-07-09 | normal | yes | yes | no | n/a | Tabs on part A keep breaking off during print. MP will give us what he has. Asking customer to see if printing in parts is ok
|  |  |  | merrill snell |  | 2018-07-11 | [5 empty] | needed later pickup b/c had a lot of parts to pack
| warner6057 | [11 empty] | log IF ext and internal on deep
done
| olsen2185 | black more inc | useless_sheep15498 | NorCal | Danielle | 2018-07-03 | normal | internal so far |  |  |  | Godspeed got confused picking up the parts from the MP. Had delayed pickup. Parts are out of spec with oversized holes. Send out
| stevenkhau-75853-A-01-A-01-A | lyft | obnoxious_alligator22568 | viking | David | 2018-06-26 | urgent | external OT | yes |  |  | material sourcing issues of large parts
| stevenkhau-75853-A-01-A-01-A | lyft | Wicked_chicken58896 | jarvis | David | 2018-06-26 | urgent | yes | yes |  | no | MP questions on model/drawing mismatch part accidentally gouged
| birkmeyer6589 | dishcraft | clever_salmon59697 | Circuit Case | Danielle | 2018-07-06 | urgent | no | yes | yes | n/a | MP received 1 qnty of part B with stripped threads. Waiting to see if helicoil installation would be ok

## 712
time in | sales order | account | work order | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
| gagne2485 | aeva | obnoxious_bear87015_feidi | shouzheng | Danielle | 2018-07-18 | very urgent | n/a | no | n/a | n/a | Check asana. | make C & D locally.
| obrien2798 | otherlab | depressed_ostrich47047_feidi | bole | Danielle | 2018-07-16 | very urgent | no |  | n/a |  | new due date: 7/19. C & G to be made locally with mcmaster. Left DO note. | Assign to local MP. Record external OT on Fictiv capacity
| parkes1339 | bellwether |  |  | Danielle |  |  | IF ext |  |  |  | AE didn't upload drawing to indicate taps. Asana set to pick up parts from customer for same-day tapping. Check asana to see which parts need this | call Swope now
| warner4580 | orca bio system | happy_rabbit37371 | KAD | Danielle | 2018-07-12 | urgent | int/ext OT | yes | yes | backorder | programming error. should be ready by noon 7/13 | send to DuAll for one day anodizing. change asana task
pending responses
| bangs5566 | lyft | irrelevant_seahorse47430 and introvert_mosquito13450 | Extreme/Maxpol | Danielle | 2018-07-16 | urgent | n/a | n/a | yes | n/a | sent to maxpol. needs extra piece to calibrate machine that we don't have. Customer ok with using one of the 20 to calibrate machine
| anselmmak-72505 | tesla | extrovert_sheep67275 | Deep Machine | Mo | 2018-07-05 | normal | yes | ? | ? | ? | water jet part. various qc issues. large CB that made hole oversized | pending customer response
production resumed
| hastings8141 | simplexity pd | infamous_salmon65296 | SW Precision | Danielle | 2018-07-12 | urgent | int/ext OT | yes | yes | no | Tool broke in a hole in the part. Needs to scrap entire part. Will be ready 7/13 | Make sure pickup is set for 7/13 for SW
| selle6431 | auris health | punctual_puppy49326 | Swiss Precision | Danielle | 2018-07-12 | urgent | int/ext OT | yes | yes | no | MP received wrong tool. will be delayed a day. Only 7 parts done on 7/13 | Move receipts & DO to tomorrow. Courier tomorrow
| oshiro1012 | kitty hawk | hypnotized_goldfish79568 | Fathom | Danielle | 2018-07-12 | urgent | int/ext OT | yes | n/a | n/a | Parts A and B have pressure cracks in them. We are receiving current print and Fathom is reprinting for tomorrow. | If Fathom's reprints look good, set pickup for tomorrow.
| stulc8482 | momentum | suspicious_seahorse30661 | Extreme | Danielle | 2018-07-16 | very urgent | n/a | yes | n/a | n/a | Drawing calls out 2x of grooves, but there's only one in the model. Let customer know of type and MP proceeded with production
| hardy9180 | rga | atomic_gnu80541-C | madon | Danielle | 2018-07-12 | normal | int/ext OT | yes | yes | n/a | Forgot to switch support material. Part C will be done eod 7/12. | Record interanl/external OTIF. Set pickup for tomorrow
| bangs3264 | lyft | drunk_marmot92489 | Maxpol | Danielle | 2018-07-17 | urgent | n/a | yes | n/a | n/a | Needs laser etching for part number and revision, but has anodizing after that may make it difficult to see. MP is engraving part number
| goodwin4678 | vector-launch | tender_penguin49682 | Sierra Pacific | Danielle | 2018-07-13 | normal | n/a | yes | n/a | n/a | MP wondering if threads go on one surfae or two on a shaft. There's a break where there's a thinner diameter. Threads go on both surfaces
| goodwin4638 | vector-launch | clumsy_coyote34223 | Mach 1 | Danielle | 2018-07-13 | very urgent | n/a | yes | n/a | n/a | MP wondering if they can increase internal radii from 0.1" to 0.125". Customer said ok.
document
| maclaren2401 | hobbit view | wandering_robin31571 | Madon | Danielle | 2018-07-09 | normal |  | n/a | yes | n/a | Support left on the part so it needed to go back in the bath. MP needed later pickup | log internal OTIF.
| agozzino6930 | lumasense inc | gullible_nuthatch48170 | fathom | Danielle | 2018-07-10 | normal | int | yes | yes | n/a
| agozzino3617 | lumasense inc | adorable_coyote44528 | fathom | Danielle | 2018-07-10 | normal | int | yes | yes | n/a
| lang6581 | propelland | wicked_chicken72262 | Radius | Danielle | 2018-07-10 | normal | no | yes | no | no | MP had blackout over weekend. Large print will be done Wednesday. Ficitv validated DO prematurely. Pickup wasn't set for Wednesday. | log internal and external OTIF on Radius and Fictiv
| mcleod2001 | bossa nova | rad_penguin75416 | Max Dirat | Danielle | 2018-07-09 | normal | yes | yes | no | n/a | Tabs on part A keep breaking off during print. MP will give us what he has. Asking customer to see if printing in parts is ok
|  |  |  | merrill snell |  | 2018-07-11 | [5 empty] | needed later pickup b/c had a lot of parts to pack. Lot internal for all jobs due to madon 7/11
| warner6057 | orca bio systems | obnoxious_falcon56721-B | deep machine |  | 2018-07-11 | urgent |  | yes | yes | n/a | Oversized diameter that customer was ok with. | log IF ext and internal on deep
| mcdaid5992 | kitty hawk | rad_orca84521_feidi | bole | Danielle | 2018-07-19 | urgent | no | yes | n/a | no | Rona said this would be late due to Fictiv capacity. Ship date for 7/23 | log int/ext OT on Fictiv capacity
done
| sweet1206 | apple | enchanting_ram65551 | mach 1 | David | 2018-07-11 | very urgent | yes | yes | n/a | no | 3mm posts are undersized, measuring 2.85mm
| hong8197 | gmail | executive_sheep13537 | Moddler | Danielle | 2018-07-12 | normal | n/a | n/a | yes | n/a | Had surface issues. Rerouted to Fictiv to personally check. Passed our QC
| sanabria4666 | molekule | obnoxious_owl37371 | Moddler | Danielle | 2018-07-12 | normal | n/a | n/a | yes | n/a | Had surface issues. Rerouted to Fictiv to personally check. Passed our QC
| molina7792 | fictiv | happy_ram78965-B | Justin | Danielle | 2018-07-12 | normal | n/a | yes | yes | n/a | Part B file is not meshable so can't print. CSMs reached out to customer for new file. Not printing again.

## 713
time in | sales order | account | work order | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
| gagne2485 | aeva | obnoxious_bear87015_feidi | shouzheng | Danielle | 2018-07-18 | very urgent | n/a | no | n/a | n/a | Check asana. At risk | make C & D locally.
| obrien2798 | otherlab | depressed_ostrich47047_feidi | bole | Danielle | 2018-07-16 | very urgent | no |  | n/a |  | new due date: 7/19. C & G to be made locally with mcmaster. Left DO note. | Assign to local MP. Record external OT on Fictiv capacity
pending responses
| anselmmak-72505 | tesla | extrovert_sheep67275 | Deep Machine | Mo | 2018-07-05 | normal | yes | ? | ? | ? | water jet part. various qc issues. large CB that made hole oversized | pending customer response
| oshiro1012 | kitty hawk | hypnotized_goldfish79568 | Fathom | Danielle | 2018-07-12 | urgent | int/ext OT | yes | n/a | n/a | Parts A and B have pressure cracks in them. We are receiving current print and Fathom is reprinting for tomorrow. | pending response from MP
production resumed
| bangs5566 | lyft | irrelevant_seahorse47430 and introvert_mosquito13450 | Extreme/Maxpol | Danielle | 2018-07-16 | urgent | n/a | n/a | yes | n/a | sent to maxpol. needs extra piece to calibrate machine that we don't have. Customer ok with using one of the 20 to calibrate machine. Extreme doing dowel pin installation
| selle6431 | auris health | punctual_puppy49326 | Swiss Precision | Danielle | 2018-07-12 | urgent | int/ext OT | yes | yes | no | MP received wrong tool. will be delayed a day. Only 7 parts done on 7/13 | Move receipts & DO to tomorrow. Courier tomorrow
| marsot3339 | auris | excited_ostrich27843 | CalPol | Danielle | 2018-07-13 | urgent | int OT | yes | yes | n/a | Wasn't ready for pickup b/c tight tolerance. Had to scrap some parts.
| espinosa9269 | vector-launch | hungry_bear72701 | RYT | David | 2018-07-17 | normal | no | yes | yes | yes | Lead time too tight due to material sourcing. Will be ready eod 7/19
| warner4580 | orca bio system | happy_rabbit37371 | KAD | Danielle | 2018-07-16 | urgent | int/ext OT | yes | yes | backorder | programming error. should be ready by noon 7/13. Send to DuAll on 7/13 for one-day ano
| stulc8482 | momentum | suspicious_seahorse30661 | Extreme | Danielle | 2018-07-16 | very urgent | n/a | yes | n/a | n/a | Drawing calls out 2x of grooves, but there's only one in the model. Let customer know of type and MP proceeded with production
| bangs3264 | lyft | drunk_marmot92489 | Maxpol | Danielle | 2018-07-17 | urgent | n/a | yes | n/a | n/a | Needs laser etching for part number and revision, but has anodizing after that may make it difficult to see. MP is engraving part number
| goodwin4678 | vector-launch | tender_penguin49682 | Sierra Pacific | Danielle | 2018-07-23 | normal | n/a | yes | n/a | n/a | MP wondering if threads go on one surfae or two on a shaft. There's a break where there's a thinner diameter. Threads go on both surfaces
| mcdaid5992 | kitty hawk | rad_orca84521_feidi | bole | Danielle | 2018-07-19 | urgent | no | yes | n/a | no | Rona said this would be late due to Fictiv capacity. Ship date for 7/23 | log int/ext OT on Fictiv capacity
| goodwin4638 | vector-launch | clumsy_coyote34223 | Mach 1 | Danielle | 2018-07-26 | very urgent | n/a | yes | n/a | n/a | MP wondering if they can increase internal radii from 0.1" to 0.125". Customer said ok.
document
done
| mcleod2001 | bossa nova | rad_penguin75416 | Max Dirat | Danielle | 2018-07-09 | normal | yes | yes | no | n/a | Tabs on part A keep breaking off during print. MP will give us what he has. Asking customer to see if printing in parts is ok
| hardy9180 | rga | atomic_gnu80541-C | madon | Danielle | 2018-07-12 | normal | int/ext OT | yes | yes | n/a | Forgot to switch support material. Part C will be done eod 7/12. | Record interanl/external OTIF. Set pickup for tomorrow
| oshiro5822 |  |  | sculpteo | Danielle | 2018-07-13 |  | int/ext OT | yes | yes | n/a |  | log int/ext OT
|  |  |  | merrill snell |  | 2018-07-11 |  | int OT |  |  |  | needed later pickup b/c had a lot of parts to pack. Lot internal for all jobs due to madon 7/11
| lugo3495 | jpl | infamous_flamingo85167-D | V3 | Danielle | 2018-07-13 | urgent | int OT | n/a | yes | n/a | need more time to machine part D
| maclaren2401 | hobbit view | wandering_robin31571 | Madon | Danielle | 2018-07-09 | normal | int OT | n/a | yes | n/a | Support left on the part so it needed to go back in the bath. MP needed later pickup
| parkes1339 | bellwether |  |  | Danielle |  |  | IF ext |  |  |  | AE didn't upload drawing to indicate taps. Asana set to pick up parts from customer for same-day tapping. At Circuit Case. MP didn't have right tap so we sent back to custoemr
| hastings8141 | simplexity pd | infamous_salmon65296 | SW Precision | Danielle | 2018-07-12 | urgent | int/ext OT | yes | yes | no | Tool broke in a hole in the part. Needs to scrap entire part. Will be ready 7/13
| warner6057 | orca bio systems | obnoxious_falcon56721-B | deep machine |  | 2018-07-11 | urgent | int/ext IF | yes | yes | n/a | Oversized diameter that customer was ok with. | log IF ext and internal on deep
| lang6581 | propelland | wicked_chicken72262 | Radius | Danielle | 2018-07-10 | normal | int/ext OT | yes | no | no | MP had blackout over weekend. Large print will be done Wednesday. Ficitv validated DO prematurely. Pickup wasn't set for Wednesday.
| agozzino6930 | lumasense inc | gullible_nuthatch48170 | fathom | Danielle | 2018-07-10 | normal | int | yes | yes | n/a
| agozzino3617 | lumasense inc | adorable_coyote44528 | fathom | Danielle | 2018-07-10 | normal | int | yes | yes | n/a

## 716
time in | sales order | account | work order | MP | DRI | job due date | priority | OTIF recorded | CSMs alerted | Logistics/QC Alerted | Odoo dates changed | initial summary | action items/pending questions
action
| gagne2485 | aeva | obnoxious_bear87015_feidi | shouzheng | Danielle | 2018-07-18 | very urgent | n/a | no | n/a | n/a | Check asana. At risk | make C & D locally.
| obrien2798 | otherlab | depressed_ostrich47047_feidi | bole | Danielle | 2018-07-16 | very urgent | no |  | n/a |  | new due date: 7/19. C & G to be made locally with mcmaster. Left DO note. | Assign to local MP. Record external OT on Fictiv capacity
pending responses
| anselmmak-72505 | tesla | extrovert_sheep67275 | Deep Machine | Mo | 2018-07-05 | normal | yes | ? | ? | ? | water jet part. various qc issues. large CB that made hole oversized | pending customer response
| oshiro1012 | kitty hawk | hypnotized_goldfish79568 | Fathom | Danielle | 2018-07-12 | urgent | int/ext OT | yes | n/a | n/a | Parts A and B have pressure cracks in them. We are receiving current print and Fathom is reprinting for tomorrow. | pending response from MP
production resumed
| bangs5566 | lyft | irrelevant_seahorse47430 and introvert_mosquito13450 | Extreme/Maxpol | Danielle | 2018-07-16 | urgent | n/a | n/a | yes | n/a | sent to maxpol. needs extra piece to calibrate machine that we don't have. Customer ok with using one of the 20 to calibrate machine. Extreme doing dowel pin installation
| selle6431 | auris health | punctual_puppy49326 | Swiss Precision | Danielle | 2018-07-12 | urgent | int/ext OT | yes | yes | no | MP received wrong tool. will be delayed a day. Only 7 parts done on 7/13 | Move receipts & DO to tomorrow. Courier tomorrow
| marsot3339 | auris | excited_ostrich27843 | CalPol | Danielle | 2018-07-13 | urgent | int OT | yes | yes | n/a | Wasn't ready for pickup b/c tight tolerance. Had to scrap some parts.
| espinosa9269 | vector-launch | hungry_bear72701 | RYT | David | 2018-07-17 | normal | no | yes | yes | yes | Lead time too tight due to material sourcing. Will be ready eod 7/19
| warner4580 | orca bio system | happy_rabbit37371 | KAD | Danielle | 2018-07-16 | urgent | int/ext OT | yes | yes | backorder | programming error. should be ready by noon 7/13. Send to DuAll on 7/13 for one-day ano
| stulc8482 | momentum | suspicious_seahorse30661 | Extreme | Danielle | 2018-07-16 | very urgent | n/a | yes | n/a | n/a | Drawing calls out 2x of grooves, but there's only one in the model. Let customer know of type and MP proceeded with production
| bangs3264 | lyft | drunk_marmot92489 | Maxpol | Danielle | 2018-07-17 | urgent | n/a | yes | n/a | n/a | Needs laser etching for part number and revision, but has anodizing after that may make it difficult to see. MP is engraving part number
| goodwin4678 | vector-launch | tender_penguin49682 | Sierra Pacific | Danielle | 2018-07-23 | normal | n/a | yes | n/a | n/a | MP wondering if threads go on one surfae or two on a shaft. There's a break where there's a thinner diameter. Threads go on both surfaces
| mcdaid5992 | kitty hawk | rad_orca84521_feidi | bole | Danielle | 2018-07-19 | urgent | no | yes | n/a | no | Rona said this would be late due to Fictiv capacity. Ship date for 7/23 | log int/ext OT on Fictiv capacity
| goodwin4638 | vector-launch | clumsy_coyote34223 | Mach 1 | Danielle | 2018-07-26 | very urgent | n/a | yes | n/a | n/a | MP wondering if they can increase internal radii from 0.1" to 0.125". Customer said ok.
document
done
| mcleod2001 | bossa nova | rad_penguin75416 | Max Dirat | Danielle | 2018-07-09 | normal | yes | yes | no | n/a | Tabs on part A keep breaking off during print. MP will give us what he has. Asking customer to see if printing in parts is ok
| hardy9180 | rga | atomic_gnu80541-C | madon | Danielle | 2018-07-12 | normal | int/ext OT | yes | yes | n/a | Forgot to switch support material. Part C will be done eod 7/12. | Record interanl/external OTIF. Set pickup for tomorrow
| oshiro5822 |  |  | sculpteo | Danielle | 2018-07-13 |  | int/ext OT | yes | yes | n/a |  | log int/ext OT
|  |  |  | merrill snell |  | 2018-07-11 |  | int OT |  |  |  | needed later pickup b/c had a lot of parts to pack. Lot internal for all jobs due to madon 7/11
| lugo3495 | jpl | infamous_flamingo85167-D | V3 | Danielle | 2018-07-13 | urgent | int OT | n/a | yes | n/a | need more time to machine part D
| maclaren2401 | hobbit view | wandering_robin31571 | Madon | Danielle | 2018-07-09 | normal | int OT | n/a | yes | n/a | Support left on the part so it needed to go back in the bath. MP needed later pickup
| parkes1339 | bellwether |  |  | Danielle |  |  | IF ext |  |  |  | AE didn't upload drawing to indicate taps. Asana set to pick up parts from customer for same-day tapping. At Circuit Case. MP didn't have right tap so we sent back to custoemr
| hastings8141 | simplexity pd | infamous_salmon65296 | SW Precision | Danielle | 2018-07-12 | urgent | int/ext OT | yes | yes | no | Tool broke in a hole in the part. Needs to scrap entire part. Will be ready 7/13
| warner6057 | orca bio systems | obnoxious_falcon56721-B | deep machine |  | 2018-07-11 | urgent | int/ext IF | yes | yes | n/a | Oversized diameter that customer was ok with. | log IF ext and internal on deep
| lang6581 | propelland | wicked_chicken72262 | Radius | Danielle | 2018-07-10 | normal | int/ext OT | yes | no | no | MP had blackout over weekend. Large print will be done Wednesday. Ficitv validated DO prematurely. Pickup wasn't set for Wednesday.
| agozzino6930 | lumasense inc | gullible_nuthatch48170 | fathom | Danielle | 2018-07-10 | normal | int | yes | yes | n/a
| agozzino3617 | lumasense inc | adorable_coyote44528 | fathom | Danielle | 2018-07-10 | normal | int | yes | yes | n/a